## Lake Management Team Projects
|  | Lake Management Task Team Project Log | [5 empty] | Last Updated | 2026-07-28
Rice Lake Area Association (RLAA)
Project # | Date | Project Description | Project Owner | Status | Exp. Comp. Date | Act. Comp. Date | Next Steps | Waiting For | Comments
1 | 2009-03-14 | Recruit for Lake Management Team members | George Schneider | Completed | 2009-03-31 | 2009-06-23 | Tally Responses |  | Have 9 team members (5 board members)
2 | 2009-06-23 | Hold first team meeting | George Schneider | Completed | 2009-06-23 | 2009-06-23 |  |  | Conducted on Schneider pontoon
3 | 2009-05-30 | Assist with Sonic Solutions unit installations | Wade Quale | Completed | 2009-05-30 | 2009-05-30 | Evaluate |  | Team to recommend to purchase units or end agreement based on unit performance.
4 | 2009-06-01 | Rough Fish removal | Nika Rybinski | Completed | 2009-08-01 | 2009-07-28 | Sample Seine in Fall |  | Board to interview Jeff Riedmann as possible fisherman to remove rough fish on Rice Lake
5 | 2009-05-30 | Evaluate Sonic Solutions installations | Wade Quale | Completed | 2009-08-31 | 2009-08-27 |  |  | Removed units on 8/23; cleaned up and returned all 3 units to LWD on 8/27.
6 | 2009-07-24 | Storm Water Drain Inventory | Bill/George | In Process | 2009-11-01 |  | Review inventory w/City |  | Inventoried all drains around lake with documents and photos. Need to clarify each with respective owner (City/State).
7 | 2009-09-14 | Evaluate Aquatic Plant Survey summary rpt | LM Team | In Process | 2009-09-27 |  | Review |  | FSS completed and provided final 2009 APS reports. Board and LM Team to review and provide feedback on resuls/recommendations.
8 | 2009-09-15 | Review Rough Fish Removal with Jeff R. | Nika Rybinski | Pending | 2009-10-01 |  | Confirm |  | Decide on Fall seine event and if want to do Winter Carp removal.
9 | 2009-09-14 | Test Plant Areas in lake | Bill/George | Pending | 2010-05-31 |  | Evaluate "Chara" plants |  | 2009 APS confirms lack of plants in lake contributing to Algae blooms. Can we plant "blanket" vegetation to prevent sediment release of nutrients?
10 | 2009-09-14 | Carp Exclosure areas | George Schneider | Pending | 2010-05-31 |  | Contact Dechmann for materials |  | It appears that we need to confirm we can grow aquatic plants with the absence of carp before dedicating time/resources to planting the entire lake. Revisit setting up carp exclosure areas for 1 or 2 sites in Spring 2010.